## Sheet1
CTF Project: next steps
Tasks | Priority | Status | Deadlines | Comments | Risks/Problems we might encounter
Registration of the national programmes at the EC database | H | Started | We coud assess where we are before the end of the year. I am guessing that once we have all the info needed for the dossier for the application we can decide if we apply or keep trying to register (depending on how close we are with registration). Updated will be sen to the WG and Board leads more regularly. | At the moment we have regsitered Belgium, Spain, Hungary, Portugal, and the Nethrlands. We can also consider the Croatian specialisation (HP/Clinical Pharmacy) as registered. French authorities have agreed to register, and the Italian Ministry of health didn’t answer to SIFO's request. SIFO is working with the chamber of pharmacy to see what can be done. The team is following up now with Austria, Germany and Poland. Czech Republic and Slovakia look like will not be registered soon (as we got negative answers already). | That we don't achieve to register the 9 countries that we need. It will also depend on future COVID-19 waves.
Follow up with DG GROW | H | Started | Throghout the project | Contact DG DGrow to: get the contact of other associations that are applying and to get a clearer picture of the dossier that needs to be prepared. Probably a second call should be organised with them. In general the idea is to be more on top of DG Grow so we can get their attention. | DG Grow not beeing helpful at all or the fact that they don’t really clarify what we need for the application. Then, is there someone else we can go for support?
Repurpose the activities of CTF WG1 | H | Planning phase | November 2021 (to repurpose the WG1) and March 2022 for the WG1 deliverables (so we can give an update/remind members during the members meeting in Vienna) | CTF WG1 (with probably the support of the Steering Committee) should help the team to gather all the information needed for the dossier that will need to be submitted including the detailed information on the national programmes that haven’t been registered. The team already has some of this information on its files but DG Grow need to clarify what needs to be included. We also need to contact Rahul to check if he will be able to continue as CTF WG1 Chair | That CTF WG1 are not so active (but if not this should be done via the national boards).
Repurpose the activities of CTF WG3 | H | Planning phase | November 2021 (to repurpose the WG1) and March 2022 for the WG1 deliverables (so we can give an update/remind members during the members meeting in Vienna) | CTF WG3 will need to help the team get a proof that national authorities are on board (this needs to be explained by the EC). A clear message of the benefits of CTF should be revisited | CTF WG3 is very active in general. The problem here is that the priorities for authorites have shifted because of the pandemic (so maybe less responsive) but also there is the risk of authorities not beeing on board.
Repurpose of the activities of the CTF Steering Committee | M | Planning phase | November 2021 (depending on what you decide on this overview) | A meeting with the CTF Steering Committee could be organised in November to discuss this document and next steps. The Steering committee could support the WGs and could also help the team gather information on how's the situation of the hospital pharmacy profession across Europe (this needs to be included in the dossier). The Steering committee should help the team draft the agenda for the meeting with key national associations. | The Steering committed hasn’t been engaged in a while (we didn’t really need their input) so we might need to reactivate it.
Meeting with national associations (the ones that are more key for the project) | H | Planning phase | Second half of November 2021/Early December | We should probably organise meeting with national boards with a twofold goal: o explain to them this approach and make sure that we have their support to move forward (as we will need their help). I’d suggest to do a virtual meeting with the WG leads, the team and a representative of each national board (we don’t need all countries but the countries with a regulated or some sort of regulated specialisation). Probably CTF WG3 should also be invited as they will have to link between the national boards and authorities in some cases. | We really need to tailor the message and don't convey a pessimistic message to national associations. We need to clearly explain that DG GROW is not beeing helpful and that after a certain point we will need to apply
CTF Roadmap | M | Started | 2021-11-01 | We have about half of the information that we need from members for this, but we will get more information thanks to the dossier that needs to be prepared. As some priorities have shifted and Marta left EAHP (she was the one working on the desing of the roadmap) this hasn't been completed. But we should probably post | As this is not a priority this task was put a bit on hold but the team will work on it asap
CTF website | M | Planning phase | Before December 2021 ideally | The team (and maybe CTF WG3) should revisit the CTF website and see if an update is needed, specially now that we are approaching authorities with regard to CTF. Maybe a new flyers/brochure should be prepared | As above, this is time consuming and not priority as we don’t have a lot of resources now, thus, we could ask CTF WG3 to support the team on this.
Appling for CTF, submitting the application | M | Stuck | A decision should be made at the next EAHP Board meeting in January 2021 | Once we get the infromation from DG Grow and a clear view of the registration of the missing countries we need to decide and put a deadline to when we will apply (even if we don’t have all the countries). I'd suggest to assess this once we have all the dossiers prepared