TEMPLATE ACTION PLAN –     [FOR DISCUSSION AND AGREEMENT AT THE MEETING]

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources - Resources Available - Resources Needed (financial, human, political & other) | Potential Barriers - What individuals or organizations might resist? - How? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| 1: Research methodology for evidence to support patient outcomes and costs (cost benefit and cost of education) To include- GPI Level of evidence Proof that patient care is enhanced Cost saving/benefit Education costs Database Evidence based approach Identification of sources | Working party - Hospital pharmacists with access to co workers (Part of thesis) - Academia | After WP is set up – 6-9 months including the research (end 2015?!) | - Knowledge Contacts Access to publications - Time – human resources Travel expenses possibly | - Competing priorities - Passive resistance | Steering group – send out call for volunteers WP to report back to steering group - After the first meeting - in the middle of the planned period - for exceptional issues |
| 2: how pharmacists are trained - level of specialisation (also part of Mapping) - what influence - management structures and culture | Working party | 2nd work stream for the WP | - Country association involvement B. | A. Hospital organization Political lack of interest - Professional association - Ministry Other HCP conflicting interests Hospital Pharmacist involvement in the management structures B. | WP nominees EAHP office Collect data/opinion |
| 3: Training of other professions | WP |  | A. B. | A. B. | Collect data |
| 4: Publication | WP/Steering Committee |  | A. B. | A. B. | After point 1 |
| 5. Mobility | Steering Committee |  |  |  | Collect data |