TEMPLATE ACTION PLAN –     Creating Competencies / mapping

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources - Resources Available - Resources Needed (financial, human, political & other) | Potential Barriers - What individuals or organizations might resist? - How? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| 1: Standard template for data collection | EAHP office | By 25 january | - Many docs form many countries - National programs | - none B. | Country delegates - once |
| 2: Collect information from countries, | National institutions Professional bodies Scientific societies | Several month (before the GA?) | A.PHARMINE repository FIP, Steering group knowledge - EAHP database and members (delegates/ chairmen e.o) | - communications and non-response by individual members of working parties - not answering | Advocacy task group of EAHP |
| 3: Compare information after extraction | We Task group and coöpted experts EAHP-intern? SC-members Students Msc phase | Q2-2016 | A. B. | A. B. | Pharmacy faculties to inform for master projects within this project |
| 4: Gap analysis | See point 4 |  | A. B. | A. B. |  |
| 5:Create glossary | EAHP office: RP and Board member | Perpetuum mobile | A.all documents involved Contact FIP B. | - translation B. | Contact with FIP National delegates of EAHP |
| 6:validation of competencies/ framework | Working group | Variable To be determined at the end of the procedure | Created documents | - steering committee - General Assembly - Members of EAHP FIP | Members of EAHP FIP General Assembly Steering committee Other professional stakeholders |
| 7.accreditation | Business opportunity for EAHP |  |  | - Existing accreditation institutions - Professional partnerships - This is a political sensitive subject | Other accreditation organisations |